## Table 1
MEF Conversion Schools Startup Plan
Key
MEFED | MEF Exec Director
Treas | Treasurer, BOD
Prin | Principal
AP | Assistat Principal
DPD | Director of Professional Development
DOO | Director of Operations
MEF BOD | MEF Board of Directors
Tasks & Steps |  | Task Owner | Target Completion Date | Oct '18 | Nov '18 | Dec '18 | Jan '19 | Feb '19 | Mar '19 | Apr '19 | May '19 | June '19 | July '19 | Project Status
STAFFING | [12 empty] | SCHOOL
Hire Principal | [12 empty] | OPENS
Draft and approve advertisement/job description for Principal & |  | MEFED | Spring 2019 | X |  |  | X | [6 empty] | 0
Conduct national outreach to develop candidate pool |  | MEFED | Ongoing |  |  |  | X | X | X |  |  |  |  | 0
Make “networking” contacts to recruit candidates for Principal & |  | MEFED | Ongoing |  |  |  | X | X | X |  |  |  |  | 0
Receive and organize letters of interest and resumes |  | MEFED | Summer 2019 | X |  |  | X | X | X |  |  |  |  | 0
Organize selection committee for Principal |  | MEFED | Summer 2019 | X |  |  |  | X | [5 empty] | 0
Review applications and select candidates for interview for |  | MEFED | Summer 2019 |  | X |  |  | X | [5 empty] | 0
Schedule interviews for Principal |  | MEFED | Fall 2019 |  | X |  |  | X | [5 empty] | 0
Conduct interviews for Principal with Selection Committee |  | MEFED | Fall 2020 |  | X |  |  | X | X |  |  |  |  | 0
Identify finalists and check references |  | MEFED | Fall 2021 |  | X | X |  |  | X |  |  |  |  | 0
Schedule site visits/final on-site interview for Principal |  | MEFED | Fall 2022 |  |  | X | X |  | X |  |  |  |  | 0
Select Principal and make offer |  | MEF Board | Jan 2019 |  |  | X | X |  | X |  |  |  |  | 0
Hire Principal |  | MEF Board | Jan 2019 |  |  | X | X |  | X |  |  |  |  | 0
Recruit School Staff
Draft and approve advertisements/job descriptions for staff |  | MEFED/AP |  |  |  |  | X | [6 empty] | 0
Run ads in local and national newsletters and online job boards/sites |  | MEFED/AP |  |  |  |  | X | X | X | X |  |  |  | 0
Receive interest and applications from current school staff |  | MEFED/AP |  |  |  |  | X | X | X |  |  |  |  | 0
Reach out to staff referrals |  | MEFED/AP |  |  |  |  | X | X | X | X |  |  |  | 0
Host recruitment events (job fair, networking happy hours, etc.) |  | MEFED/AP | [5 empty] | X | X | X | X |  |  | 0
Receive and organize applications and resumes |  | MEFED/AP | [5 empty] | X | X | X | X | X |  | 0
Select School Staff
Interview and observe current school staff who are interested staying and working for IN |  | MEFED/AP | [5 empty] | X | X | X |  |  |  | 0
Identify all positions that need to be filled |  | MEFED/AP | [6 empty] | X | X | X |  |  | 0
Review applications and resumes and select candidates to interview |  | MEFED/AP | [5 empty] | X | X | X | X | X |  | 0
Conduct candidate interviews and observations |  | MEFED/AP | [5 empty] | X | X | X | X | X |  | 0
Hire School Staff
Conduct finalist interviews |  | AP | [5 empty] | X | X | X | X | X |  | 0
Check references |  | AP | [5 empty] | X | X | X | X | X |  | 0
Select staff members and make offers |  | Prin | [5 empty] | X | X | X | X | X |  | 0
Hire staff |  | Prin | [5 empty] | X | X | X | X | X |  | 0
Staff Onboarding
New staff orientations scheduled and convened |  | DPD, DOO | [8 empty] | X | X | X | 0
All on---boarding materials and paperwork is complete |  | DOO | [10 empty] | X | 0
BOY whole---school development takes place |  | AP, DPD | [10 empty] | X | 0
STUDENT & FAMILY ENGAGEMENT/RECRUITMENT
Engage Parents and Families
Host informational sessions about CMO transition |  | Prin, MEFED |  |  |  |  | X | X | [5 empty] | 0
Plan engagement activities |  | AP, MEF |  |  |  |  | X | X | [5 empty] | 0
Host parent, student, and family engagement activities |  | AP, MEF | [5 empty] | X |  | X |  | X | X | 0
Host open houses |  | AP, MEF | [9 empty] | X | X | 0
Recuit Students
Tasks & Steps |  | Task Owner | Target Completion Date | Oct '18 | Nov '18 | Dec '18 | Jan '19 | Feb '19 | Mar '19 | Apr '19 | May '19 | June '19 | July '19 | Project Status
Inform parents of current students of new operator systems, |  | MEFED, AP |  |  |  |  | X | X | [5 empty] | 0
Design, print, and distribute recruitment materials (brochures, |  | MEF, AP |  |  |  |  | X | X | X | X | X |  |  | 0
Promote school and enrollment via marketing channels (radio, |  | MEF, AP | [5 empty] | X | X | X | X | X |  | 0
Meet with community and neighborhood groups |  | MEF, AP | [5 empty] | X | X | X | X |  |  | 0
Solicit parent referrals for future students |  | AP |  |  |  |  | X | X | X | X | X |  |  | 0
Conduct community presentations and events |  | MEF, AP | [5 empty] | X | X | X | X | X |  | 0
Reach out to headstarts, preschools, and other early learning |  | MEF, AP | [5 empty] | X | X | X |  |  |  | 0
Monitor student enrollment applications against progress |  | SOM,AP | [5 empty] | X | X | X | X | X | X | 0
Enroll Students
Contact parents to complete registration documents |  | DOO | [7 empty] | X | X | X | X | 0
Host registration and open house nights |  | DOO | [7 empty] | X | X | X | X | 0
Set up student information system |  | DOO | [7 empty] | X |  |  |  | 0
Review IEP requirements of special needs students; determine |  | AP | [7 empty] | X | X | X | X | 0
Prepare final rosters for first day of school |  | DOO | [10 empty] | X | 0
Adjust rosters and enrollment counts once students arrive |  | DOO | [11 empty] | 0
Operations
Facility & Maintenance
Obtain access to facility |  | DOO | [6 empty] | X |  |  |  |  | 0
Establish utility accounts |  | DOO | [9 empty] | X |  | 0
Finalize facility agreement with district |  | DOO | [8 empty] | X |  |  | 0
Repair, clean, and paint facility (as needed) |  | DOO | [9 empty] | X | X | 0
Conduct facility assessment to determine short and long---term |  | DOO | [6 empty] | X | X |  |  |  | 0
Communicate long---term facility needs to district |  | DOO | [7 empty] | X | X |  |  | 0
Develop action plan for immediate/urgent short term needs |  | DOO | [7 empty] | X | X |  |  | 0
Finalize ongoing maintenance contract or shared service |  | DOO | [8 empty] | X | X | X | 0
Negotiate with district to resolve any immediate capital needs |  | DOO | [8 empty] | X | X |  | 0
Contract with service providers to resolve any immediate non--- |  | DOO | [9 empty] | X | X | 0
Complete immediate non---capital needs |  | DOO | [9 empty] | X | X | 0
Transportation
Finalize general transportation plan contract |  | DOO/MEF Board | [7 empty] | X |  |  |  | 0
Finalize bus contract for SPED |  | DOO/MEF Board | [7 empty] | X |  |  |  | 0
Establish bus routes based on enrollment data |  | DOO | [8 empty] | X | X |  | 0
Notify parents of bus routes/times |  | DOO | [9 empty] | X | X | 0
Trial runs for bus service |  | DOO | [11 empty] | 0
Launch bus service |  | DOO | [11 empty] | 0
Food Service
Finaliize food service contract |  | MEF Board | [7 empty] | X |  |  |  | 0
Make any modifications necessary to provide food service |  | DOO | [8 empty] | X |  |  | 0
File necessary paperwork for Free and Reduced lunch |  | DOO | [10 empty] | X | 0
Launch food service |  | DOO | [11 empty] | 0
Security
Evaluate existing alarm system (Transfer codes and system) |  | DOO | [9 empty] | X |  | 0
Tasks & Steps |  | Task Owner | Target Completion Date |  |  |  | Jan '19 | Feb '19 | Mar '19 | Apr '19 | May '19 | June '19 | July '19 | Project Status
SCHOOL
OPENS
Determine if new alarm system is needed |  | DOO | [9 empty] | X |  | 0
If new --- secure new vendor and contract |  | DOO | [10 empty] | X | 0
If new --- install new system and test system |  | DOO | [10 empty] | X | 0
If exisiting --- transfer codes and system from district |  | DOO | [10 empty] | X | 0
Finalize alarm system transfer and confirm functionality |  | DOO | [10 empty] | X | 0
Custodial
Produce RFP for Custodial contract |  | DOO | [7 empty] | X |  |  |  | 0
Finalize custodial contract |  | DOO | [8 empty] | X |  |  | 0
Finalize any ancillary contracts (trash removal, etc.) |  | DOO | [8 empty] | X |  |  | 0
Technology and Information Systems
Technology
Review current technology hardware and software |  | DOO | [8 empty] | X | X |  | 0
Conduct technology inventory |  | DOO | [8 empty] | X | X |  | 0
Determine quantities and types of various computer equipment |  | DOO | [9 empty] | X |  | 0
Provide a distribution list indicating where equipment should be |  | DOO | [9 empty] | X |  | 0
Turn over system for tracking inventory to site---based |  | DOO | [9 empty] | X | X | 0
Receive newly purchased equipment and distribute |  | DOO | [10 empty] | X | 0
Information Systems
Finalize network/hardware/server plan |  | DOO | [8 empty] | X |  |  | 0
Order equipment |  | DOO | [8 empty] | X | X |  | 0
Install equipment and set up network |  | DOO | [10 empty] | X | 0
Website
Integrate current school website with MEF site |  | DOO | [8 empty] | X | X |  | 0
Determine basic website content |  | DOO | [8 empty] | X | X |  | 0
All website content updated |  | DOO | [10 empty] | X | 0
E---Rate
Finalize e---rate application manager |  | DOO | [8 empty] | X |  |  | 0
Submit initial e---rate application |  | DOO | [9 empty] | X |  | 0
PROCUREMENT
Order and Delivery of Materials
Identify core materials that need to be ordered furniture materials |  | SOM, DPD | [7 empty] | X | X | X |  | 0
Deterine what curriculum and instructional materials area |  | AP, DPD | [6 empty] | X | X | X |  |  | 0
Arrange for placement of orders for required books and |  | DOO/DPD | [8 empty] | X | X |  | 0
Determine projected delivery dates for texts and materials |  | DOO/DPD | [8 empty] | X | X |  | 0
Identify texts and materials that are on backorder; make |  | DOO/DPD | [8 empty] | X |  |  | 0
Apprise staff of materials delivery plans, including |  | DOO | [10 empty] | X | 0
Plan for delivery of materials to the school site; determine |  | DOO | [10 empty] | X | 0
Establish system for tracking delivery of materials to site and |  | DOO | [9 empty] | X | X | 0
Confirm delivery of instructional materials on site |  | DOO | [10 empty] | X | 0
Instructional materials distributed and ready for use on site |  | DOO/DPD | [10 empty] | X | 0
PROFESSIONAL DEVELOPMENT
Beginning of Year Planning and Training
Train new principal and AsstPs during summer intensive |  | AP/DPD | [8 empty] | X | X |  | 0
Tasks & Steps |  | Task Owner | Target Completion Date |  |  |  | Jan '19 | Feb '19 | Mar '19 | Apr '19 | May '19 | June '19 | July '19 | Project Status
Determine network PD plan and schedule for year |  | AP/DPD | [6 empty] | X | X | X |  |  | 0
Determine school PD plan and schedule for year |  | MEF/AP | [6 empty] | X | X | X |  |  | 0
Arrange for materials, equipment for PD |  | DOO/DPD | [8 empty] | X | X |  | 0
Develop schedule for pre---opening professional development |  | AP/DPD | [8 empty] | X | X |  | 0
Communicate schedule and plan for professional development |  | AP/DPD | [9 empty] | X | X | 0
Conduct professional development |  | DPD, AP | [10 empty] | X | 0